## 📋 Summary
🏥 Hospital Management System
Product Backlog · Version 2.0
21 Epics · 120+ Features · 4 Delivery Phases · 10 Sprints
117 | 1232 | 79 | 28 | 10 | 21 | 10
Total Features | Story Points | Must Have | Should Have | Could Have | Epics | Sprints
Phase | Description |  | Sprints | Epics | Features | Story Points
Phase 1 | Foundation & Core Workflows |  | 1–2 | 6 | 14 | 155
Phase 2 | Clinical Modules & Pharmacy |  | 3–4 | 9 | 34 | 340
Phase 3 | LIS, Billing Extensions & EMR |  | 5–7 | 10 | 36 | 318
Phase 4 | Advanced & Integration Layer |  | 8–10 | 11 | 33 | 419
PRIORITY LEGEND
Must Have |  | Should Have |  | Could Have

## 📦 Product Backlog
Epic ID | Epic Name | Feature ID | Feature Name | Priority | Complexity | Story Points | Status | Phase | Target Sprint | Acceptance Criteria | Dependencies | Notes / Context
EPIC-01 | Patient Management | F-01-01 | Patient Registration & UHID Generation | Must Have | High | 21 | Not Started | Phase 1 | Sprint 1 | Patient registered with UHID; duplicate check triggered; confirmation SMS sent | — | Core registration with auto UHID generation
|  | F-01-02 | Patient Search & Advanced Filter | Must Have | Medium | 8 | Not Started | Phase 1 | Sprint 1 | Search returns results within 1 sec; filters by DOB, gender, ward | F-01-01 | Quick search by name / phone / UHID
|  | F-01-03 | Patient Demographics Management | Must Have | Medium | 13 | Not Started | Phase 1 | Sprint 2 | All demographic fields editable; change history stored | F-01-01 | Complete patient profile management
|  | F-01-04 | Merge Duplicate Patient Records | Should Have | High | 8 | Not Started | Phase 2 | Sprint 3 | Admin can merge two records; audit log captures action | F-01-01, F-01-03 | Admin function for deduplication
|  | F-01-05 | Patient Photo & Document Upload | Could Have | Low | 5 | Not Started | Phase 2 | Sprint 4 | Supports JPEG/PNG/PDF; max 10 MB; linked to patient record | F-01-01 | Attach photos and supporting documents
EPIC-02 | Appointment System | F-02-01 | Doctor Schedule Configuration | Must Have | High | 13 | Not Started | Phase 1 | Sprint 2 | Doctor sets weekly template; exception days blocked | F-01-01, F-13-01 | Weekly schedule with time slot setup
|  | F-02-02 | Online Appointment Booking | Must Have | Medium | 13 | Not Started | Phase 1 | Sprint 2 | Patient books within 3 steps; confirmation shown & emailed | F-02-01 | Patient-facing portal booking
|  | F-02-03 | Walk-in Registration & Token Generation | Must Have | Medium | 8 | Not Started | Phase 1 | Sprint 2 | Token printed in < 10 sec; queue display updated | F-02-01 | Reception desk quick registration
|  | F-02-04 | Appointment Rescheduling & Cancellation | Should Have | Low | 5 | Not Started | Phase 2 | Sprint 3 | Reschedule/cancel available up to 2 h before appointment | F-02-02, F-02-03 | Self-service and reception-managed
|  | F-02-05 | SMS/Email Appointment Reminders | Could Have | Medium | 8 | Not Started | Phase 3 | Sprint 5 | Reminder sent 24 h and 2 h before appointment | F-02-02, F-02-03 | Integration with SMS gateway
|  | F-02-06 | Appointment Waitlist Management | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 3 | Waitlisted patient auto-notified on cancellation slot | F-02-02 | Auto-promote from waitlist on cancellation
|  | F-02-07 | Doctor Leave Management | Must Have | Medium | 8 | Not Started | Phase 1 | Sprint 2 | Leave blocks slots; patients on those dates get alternate options | F-02-01 | Block slots during leave; auto-notify patients
|  | F-02-08 | QR Code Check-in | Should Have | Medium | 5 | Not Started | Phase 3 | Sprint 5 | QR scan updates check-in status in < 3 sec | F-02-03 | Self check-in at reception kiosks
|  | F-02-09 | Online Payment During Booking | Could Have | Low | 8 | Not Started | Phase 3 | Sprint 6 | Payment gateway returns success/failure; booking confirmed on success | F-02-02 | Payment gateway integration for prepaid bookings
EPIC-03 | OPD Management | F-03-01 | Patient Queue Management with Display Board | Must Have | Medium | 13 | Not Started | Phase 1 | Sprint 2 | Queue board updates in real-time; token called via audio/visual | F-02-03 | Digital queue board for waiting area
|  | F-03-02 | Clinical Documentation (SOAP Notes) | Must Have | High | 21 | Not Started | Phase 2 | Sprint 3 | SOAP notes saved per visit; previous notes read-only | F-03-01, F-16-01 | Core EMR – Subjective/Objective/Assessment/Plan
|  | F-03-03 | Vital Signs Recording | Must Have | Low | 5 | Not Started | Phase 2 | Sprint 3 | Vitals recorded with timestamp; out-of-range values flagged | F-03-01 | BP, Temp, Pulse, SPO2, Weight, Height
|  | F-03-04 | e-Prescription Writing | Must Have | High | 13 | Not Started | Phase 2 | Sprint 3 | Prescription contains drug, dose, frequency, duration; PDF printable | F-03-02, F-07-01 | With integrated drug database
|  | F-03-05 | ICD-10 Code Integration | Should Have | Medium | 8 | Not Started | Phase 2 | Sprint 4 | Diagnosis linked to ICD-10 code; code searchable by keyword | F-03-02 | Diagnosis coding for billing & reporting
|  | F-03-06 | Diagnosis & Prescription Templates | Should Have | Medium | 8 | Not Started | Phase 2 | Sprint 4 | Doctor saves template; reuses in one click | F-03-04 | Doctor-specific reusable templates
|  | F-03-07 | Clinical Pathways | Should Have | High | 13 | Not Started | Phase 3 | Sprint 6 | Pathway steps shown with evidence level; completion tracked | F-03-02 | Evidence-based care pathway guidance
|  | F-03-08 | Referral Management | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 4 | Referral letter generated; receiving doctor notified | F-03-02 | Internal & external specialist referrals
|  | F-03-09 | Follow-up Scheduling from OPD | Must Have | Low | 5 | Not Started | Phase 2 | Sprint 3 | Follow-up date set; reminder triggered 24 h before | F-03-02, F-02-01 | Auto-schedule next visit after consultation
|  | F-03-10 | Procedure Recording | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 4 | Procedure recorded with CPT code; charge auto-added to bill | F-03-02, F-08-01 | Minor procedures during OPD visit
EPIC-04 | Inpatient Management | F-04-01 | Bed Management Dashboard | Must Have | High | 21 | Not Started | Phase 2 | Sprint 4 | Dashboard shows occupied/available/reserved beds per ward | F-15-03 | Real-time bed status across wards
|  | F-04-02 | Admission Process (Emergency/Planned) | Must Have | High | 13 | Not Started | Phase 2 | Sprint 4 | Admission form complete with consent; bed allocated | F-01-01, F-04-01 | Full admission workflow with consent forms
|  | F-04-03 | Ward Management & Bed Transfer | Must Have | Medium | 13 | Not Started | Phase 2 | Sprint 4 | Transfer recorded; nursing team notified; bed freed | F-04-02 | Transfer between wards/rooms
|  | F-04-04 | Discharge Summary Generation | Must Have | Medium | 13 | Not Started | Phase 3 | Sprint 5 | Discharge summary auto-filled from notes; signed off by doctor | F-03-02, F-04-02 | Auto-populated from clinical records
|  | F-04-05 | Death Certificate Module | Should Have | Low | 5 | Not Started | Phase 3 | Sprint 6 | Certificate follows prescribed format; digital signature supported | F-04-02 | Standardised death certificate printing
EPIC-05 | Laboratory Information System | F-05-01 | Lab Test Catalog Setup | Must Have | High | 8 | Not Started | Phase 3 | Sprint 5 | All standard tests configured with reference ranges | — | All test parameters and reference ranges
|  | F-05-02 | Lab Order Entry (Internal/External) | Must Have | High | 13 | Not Started | Phase 3 | Sprint 5 | Orders linked to patient; TAT clock starts on order | F-05-01 | Order from OPD/IPD or walk-in
|  | F-05-03 | Sample Collection & Barcode System | Must Have | High | 13 | Not Started | Phase 3 | Sprint 5 | Barcode label printed on sample collection; tracked through processing | F-05-02 | Barcode label printing and tracking
|  | F-05-04 | Result Entry & Verification (Dual Sign-off) | Must Have | Medium | 13 | Not Started | Phase 3 | Sprint 6 | Result verified by pathologist before release; audit trail kept | F-05-03 | Technician entry + pathologist verification
|  | F-05-05 | Lab Report Generation (PDF) | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 6 | PDF report branded; sent to patient portal on verification | F-05-04 | Branded PDF with digital signature
|  | F-05-06 | Machine Interfacing (ASTM/HL7) | Should Have | High | 21 | Not Started | Phase 4 | Sprint 8 | Analyzer results auto-imported; manual override possible | F-05-03 | Bi-directional analyzer integration
|  | F-05-07 | Reference Range Management | Must Have | Medium | 5 | Not Started | Phase 3 | Sprint 5 | Age/gender-specific ranges applied automatically | F-05-01 | Age/gender specific normal ranges
|  | F-05-08 | Critical Value Alerts | Must Have | Medium | 5 | Not Started | Phase 3 | Sprint 6 | Critical value triggers notification to ordering doctor within 5 min | F-05-04 | Auto-alert clinician on critical results
|  | F-05-09 | Delta Check Validation | Should Have | High | 8 | Not Started | Phase 4 | Sprint 8 | Delta flag shown on result entry if change exceeds threshold | F-05-04 | Flag abnormal change from previous result
|  | F-05-10 | Lab Quality Control Module | Should Have | High | 13 | Not Started | Phase 4 | Sprint 9 | QC run logged; Levey-Jennings chart visible per analyte | F-05-04 | Levey-Jennings charts, QC runs
EPIC-06 | Radiology Management | F-06-01 | Radiology Order Management | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 6 | Orders placed with modality and priority; radiographer notified | F-15-03 | Order, track and prioritise radiology studies
|  | F-06-02 | DICOM/PACS Integration | Should Have | High | 21 | Not Started | Phase 4 | Sprint 10 | DICOM images viewable in-browser; linked to patient record | F-06-01 | Viewer integration for DICOM images
|  | F-06-03 | Radiology Reporting Template | Must Have | Medium | 13 | Not Started | Phase 4 | Sprint 7 | Template pre-fills common findings; free-text addable | F-06-01 | Structured body-part templates
EPIC-07 | Pharmacy Management | F-07-01 | Drug Master Database | Must Have | High | 13 | Not Started | Phase 2 | Sprint 3 | Drug master includes generic name, brand, strength, form, HSN | — | Generic + brand, formulation, strength
|  | F-07-02 | Stock Management (GRN, Expiry Tracking) | Must Have | High | 21 | Not Started | Phase 2 | Sprint 3 | GRN recorded; stock updated; near-expiry items flagged | F-07-01 | FIFO dispensing, expiry alerts
|  | F-07-03 | Prescription Dispensing | Must Have | High | 13 | Not Started | Phase 2 | Sprint 4 | Prescription dispensed item by item; stock decremented real-time | F-07-02, F-03-04 | Partial dispensing, substitution workflow
|  | F-07-04 | Purchase Order Management | Should Have | Medium | 13 | Not Started | Phase 3 | Sprint 5 | PO created, approved, sent to supplier; matched on GRN | F-07-01 | PO creation, approval, GRN matching
|  | F-07-05 | Supplier Management | Should Have | Low | 5 | Not Started | Phase 3 | Sprint 5 | Supplier master with GST, bank, rate-contract details | F-07-04 | Supplier master with rate contracts
|  | F-07-06 | Generic ↔ Brand Mapping | Must Have | Medium | 5 | Not Started | Phase 2 | Sprint 3 | Pharmacist can substitute generic; doctor notified | F-07-01 | Allow therapeutic substitution
|  | F-07-07 | Drug Interaction Warning | Must Have | High | 13 | Not Started | Phase 2 | Sprint 4 | Interaction warning shown before dispensing; override with reason | F-07-01, F-07-03 | Real-time interaction check at dispensing
|  | F-07-08 | Controlled Drug Tracking | Must Have | High | 8 | Not Started | Phase 2 | Sprint 4 | Controlled drug entry requires dual authentication | F-07-03 | Schedule H/X register, narcotic log
|  | F-07-09 | Auto Reorder Level Alerts | Must Have | Medium | 5 | Not Started | Phase 3 | Sprint 5 | Alert triggered when stock < reorder qty; PO suggestion generated | F-07-02 | Alert when stock < reorder quantity
|  | F-07-10 | Expiry & Near-Expiry Alerts | Must Have | Low | 5 | Not Started | Phase 2 | Sprint 4 | Dashboard shows drugs expiring in 30/60/90 days | F-07-02 | 30/60/90-day expiry dashboard
EPIC-08 | Billing & Finance | F-08-01 | OPD Billing & Receipt | Must Have | Medium | 13 | Not Started | Phase 1 | Sprint 2 | Bill generated after OPD; receipt printed; payment confirmed | F-01-01, F-02-03 | Consultation, lab, pharmacy line items
|  | F-08-02 | IPD Billing (Daily & Discharge) | Must Have | High | 21 | Not Started | Phase 2 | Sprint 4 | Daily bill available during stay; final bill at discharge | F-04-02, F-08-01 | Room charges, nursing, procedure billing
|  | F-08-03 | Payment Collection (Multi-Mode) | Must Have | Medium | 8 | Not Started | Phase 1 | Sprint 2 | All payment modes recorded; split payment supported | F-08-01 | Cash, card, UPI, cheque, online
|  | F-08-04 | Refund Processing | Should Have | Low | 5 | Not Started | Phase 3 | Sprint 6 | Refund approved by supervisor; original receipt voided | F-08-03 | Partial and full refund with approval
|  | F-08-05 | Corporate / Insurance Billing (TPA) | Must Have | High | 21 | Not Started | Phase 3 | Sprint 6 | TPA bill formatted per insurer; submitted electronically | F-08-02, F-20-01 | Credit billing, TPA claim submission
|  | F-08-06 | Package & Bundle Billing | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 5 | Package selected at admission; inclusions auto-billed | F-08-01 | Fixed-price package with inclusions
|  | F-08-07 | Discount & Concession Management | Must Have | Medium | 5 | Not Started | Phase 2 | Sprint 3 | Discount requires approval above threshold; recorded in audit | F-08-01 | Role-based discount approval workflow
|  | F-08-08 | Credit & Advance Payment Management | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 4 | Advance payment recorded against patient; adjusted at discharge | F-08-03 | Advance deposit, running ledger
EPIC-09 | Surgery & OT | F-09-01 | OT Scheduling & Booking | Must Have | High | 13 | Not Started | Phase 4 | Sprint 7 | OT booked with surgeon, anaesthetist, theatre, equipment list | F-04-02, F-02-01 | Theatre allocation, surgeon, anaesthetist
|  | F-09-02 | Surgery Notes & WHO Safety Checklist | Must Have | Medium | 13 | Not Started | Phase 4 | Sprint 7 | WHO checklist completed before incision; electronically signed | F-09-01 | Pre/intra/post-operative documentation
|  | F-09-03 | Anaesthesia Record | Should Have | Medium | 8 | Not Started | Phase 4 | Sprint 8 | Anaesthesia chart records agent, dosage, vitals every 5 min | F-09-01 | Drug doses, vitals chart, recovery notes
EPIC-10 | Nursing Module | F-10-01 | Nursing Assessment Forms | Must Have | Medium | 13 | Not Started | Phase 2 | Sprint 4 | Assessment completed at admission; auto-saved every 30 sec | F-04-02 | Admission nursing assessment
|  | F-10-02 | Medication Administration Record (MAR) | Must Have | High | 13 | Not Started | Phase 2 | Sprint 4 | MAR shows all ordered medications; each administration signed | F-03-04, F-04-02 | eMAR with scan-and-administer workflow
|  | F-10-03 | Vital Signs Charting (Trend View) | Must Have | Low | 8 | Not Started | Phase 2 | Sprint 4 | Vitals plotted on trend graph; abnormal values highlighted | F-04-02 | Graphical trends for ward vitals
|  | F-10-04 | Fluid Balance Chart | Should Have | Medium | 8 | Not Started | Phase 3 | Sprint 5 | Fluid in/out recorded per shift; daily balance calculated | F-10-01 | Intake/output monitoring
EPIC-11 | Blood Bank | F-11-01 | Donor Management | Should Have | Medium | 8 | Not Started | Phase 4 | Sprint 9 | Donor registered; donation history tracked; deferral flagged | — | Donor registry, donation history
|  | F-11-02 | Blood Inventory & Screening | Must Have | High | 13 | Not Started | Phase 4 | Sprint 9 | Blood units inventoried by component, type, expiry | F-11-01 | Component-wise stock with expiry
|  | F-11-03 | Cross Matching & Transfusion Record | Must Have | High | 13 | Not Started | Phase 4 | Sprint 9 | Cross-match result recorded; transfusion unit linked to patient | F-11-02 | ABO/Rh cross-match, transfusion log
EPIC-12 | Emergency & Triage | F-12-01 | Emergency Patient Registration | Must Have | Medium | 5 | Not Started | Phase 3 | Sprint 5 | Triage registration < 2 min; allergy and chief complaint captured | — | Quick registration (< 2 min)
|  | F-12-02 | Triage Assessment (CTAS/ESI) | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 5 | Triage score assigned; colour band printed; timer started | F-12-01 | Colour-coded triage with timer
EPIC-13 | HR & Staff Management | F-13-01 | Employee Master | Must Have | Medium | 8 | Not Started | Phase 1 | Sprint 1 | Employee record with department, designation, contact, documents | — | Staff profiles, departments, designations
|  | F-13-02 | Attendance Management | Should Have | Medium | 13 | Not Started | Phase 4 | Sprint 8 | Biometric punches synced; shift-wise report generated | F-13-01 | Biometric device integration
|  | F-13-03 | Leave Management | Should Have | Low | 8 | Not Started | Phase 4 | Sprint 8 | Leave applied and approved via workflow; balance updated | F-13-01 | Leave request, approval workflow
EPIC-14 | Reports & Analytics | F-14-01 | Daily Collection Report | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 3 | Report shows collections by mode, department, doctor; exportable | F-08-03 | Revenue collection by payment mode
|  | F-14-02 | MIS Executive Dashboard | Must Have | High | 13 | Not Started | Phase 3 | Sprint 6 | Dashboard refreshes hourly; drill-down to department level | F-14-01, F-04-01, F-08-02 | KPIs: OPD, IPD, Revenue, Occupancy
|  | F-14-03 | Occupancy & Revenue Reports | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 6 | Occupancy % and revenue per bed class shown daily | F-04-01, F-08-02 | Bed occupancy, ward-wise revenue
|  | F-14-04 | Custom Report Builder | Could Have | High | 21 | Not Started | Phase 4 | Sprint 10 | User drags fields to build report; result exportable to Excel/PDF | F-14-01, F-14-02 | Drag-and-drop ad-hoc reporting
|  | F-14-05 | Doctor Revenue & Productivity Report | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 6 | Doctor-wise OPD/IPD counts and revenue compared month-on-month | F-08-01, F-08-02 | Per-doctor OPD/IPD revenue
|  | F-14-06 | Patient Visit Trends | Should Have | Medium | 5 | Not Started | Phase 4 | Sprint 7 | Visit trend chart by specialty and patient type; filterable | F-01-01, F-02-03 | Monthly/seasonal visit pattern analysis
|  | F-14-07 | Pharmacy Sales Analytics | Must Have | Medium | 8 | Not Started | Phase 4 | Sprint 7 | Top 20 drugs by sales; slow-moving and near-expiry highlighted | F-07-03 | Top drugs, margin, movement analysis
|  | F-14-08 | Lab Revenue Analytics | Must Have | Medium | 5 | Not Started | Phase 4 | Sprint 7 | Test-wise volume and revenue; TAT compliance report | F-05-05 | Test-wise revenue and TAT
EPIC-16 | Electronic Medical Records (EMR) | F-16-01 | Longitudinal Patient Medical History | Must Have | High | 13 | Not Started | Phase 3 | Sprint 5 | All visits shown in timeline; lab, imaging, Rx accessible | F-01-01 | Unified view across all visits
|  | F-16-02 | Allergy Management | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 3 | Allergy recorded with reaction type; alert shown at prescribing | F-01-01 | Drug & food allergy with alert
|  | F-16-03 | Chronic Disease Management | Must Have | High | 13 | Not Started | Phase 3 | Sprint 6 | Chronic conditions tracked with readings and targets | F-16-01 | Ongoing condition tracking & goals
|  | F-16-04 | Clinical Attachments & Scanned Records | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 5 | Documents stored securely; retrievable by date, type | F-01-01 | Upload & link external documents
|  | F-16-05 | Patient Timeline View | Should Have | Medium | 13 | Not Started | Phase 4 | Sprint 7 | Events plotted chronologically; filterable by event type | F-16-01 | Chronological clinical event view
EPIC-17 | Patient Portal | F-17-01 | Patient Login & Profile | Should Have | Medium | 13 | Not Started | Phase 4 | Sprint 8 | OTP login via mobile; profile editable by patient | F-01-01 | OTP-based secure login
|  | F-17-02 | View Prescriptions Online | Should Have | Low | 8 | Not Started | Phase 4 | Sprint 8 | Prescriptions listed by date; downloadable as PDF | F-17-01, F-03-04 | Read-only e-prescription access
|  | F-17-03 | View & Download Lab Reports | Should Have | Low | 8 | Not Started | Phase 4 | Sprint 8 | Lab reports listed; downloaded only after pathologist release | F-17-01, F-05-05 | PDF download from portal
|  | F-17-04 | Download Invoices & Receipts | Should Have | Low | 5 | Not Started | Phase 4 | Sprint 8 | All invoices accessible; PDF download available | F-17-01, F-08-01 | Billing history and receipts
|  | F-17-05 | Online Payment via Portal | Should Have | Medium | 13 | Not Started | Phase 4 | Sprint 9 | Payment via gateway; receipt generated; outstanding updated | F-17-01, F-08-03 | Pay outstanding bills online
|  | F-17-06 | Telemedicine Consultation | Could Have | High | 21 | Not Started | Phase 4 | Sprint 10 | Video call initiated; e-prescription issued post-consult | F-17-01, F-02-02 | Video consult with e-prescription
EPIC-18 | Doctor Portal | F-18-01 | Doctor Dashboard | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 4 | Dashboard shows today's appointments, pending tasks, notifications | F-15-01 | Appointment list, pending tasks
|  | F-18-02 | Daily Appointment List | Must Have | Low | 5 | Not Started | Phase 2 | Sprint 4 | Appointment list sortable by time; patient summary on hover | F-02-01 | Today's schedule with patient summary
|  | F-18-03 | Patient History Review | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 4 | Past visits, labs, imaging accessible in 2 clicks | F-16-01 | Quick access to past visits/labs
|  | F-18-04 | e-Prescription Templates | Must Have | Medium | 8 | Not Started | Phase 2 | Sprint 4 | Favourite Rx saved and recalled by template name | F-03-04 | Favourite drug combos saved
|  | F-18-05 | Voice-to-Text Clinical Notes | Could Have | High | 13 | Not Started | Phase 4 | Sprint 9 | Voice note transcribed within 5 sec; editable before save | F-03-02 | AI-assisted speech recognition
EPIC-19 | Inventory Management | F-19-01 | Medical Consumable Inventory | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 5 | Consumable stock tracked per ward; reorder alert configured | F-15-03 | Track consumables by ward/dept
|  | F-19-02 | Store Requisition | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 5 | Department requests stock; store manager approves | F-19-01 | Department request to central store
|  | F-19-03 | Inter-Store Transfer | Should Have | Medium | 5 | Not Started | Phase 3 | Sprint 6 | Stock transferred with reason; both stores updated | F-19-01 | Move stock between stores
|  | F-19-04 | Stock Adjustment | Must Have | Low | 5 | Not Started | Phase 3 | Sprint 5 | Adjustment recorded with reason; stock updated; approved by manager | F-19-01 | Write-off, damage, correction entries
|  | F-19-05 | Purchase Requisition | Must Have | Medium | 8 | Not Started | Phase 3 | Sprint 5 | PR raised by dept; routed to purchase team for PO | F-19-01 | Dept-initiated purchase request
|  | F-19-06 | Vendor Comparison & Rate Contract | Should Have | Medium | 8 | Not Started | Phase 4 | Sprint 7 | Multiple vendor quotes compared; rate contract approved and saved | F-07-05, F-19-05 | Compare quotes, approve rate contracts
EPIC-20 | Insurance & TPA | F-20-01 | Insurance Company Master | Must Have | Low | 5 | Not Started | Phase 3 | Sprint 5 | Insurer master with scheme, covered services, limits | F-15-03 | Insurer, scheme, coverage config
|  | F-20-02 | Pre-Authorization Request | Must Have | High | 13 | Not Started | Phase 3 | Sprint 6 | PA request sent digitally; approval tracked with TAT | F-04-02, F-20-01 | Digital PA submission and tracking
|  | F-20-03 | Claim Processing & Submission | Must Have | High | 13 | Not Started | Phase 4 | Sprint 7 | Claim document bundle created; submitted per insurer format | F-08-05, F-20-02 | Claim packaging per insurer format
|  | F-20-04 | Claim Tracking & Status | Must Have | Medium | 8 | Not Started | Phase 4 | Sprint 7 | Claim status updated from insurer portal or manual entry | F-20-03 | Track submitted/pending/settled claims
|  | F-20-05 | Settlement & Reconciliation | Must Have | Medium | 8 | Not Started | Phase 4 | Sprint 8 | Settlement matched to bank receipt; balance billed to patient | F-20-04 | Bank receipt matching, balance dues
EPIC-21 | Mobile Applications | F-21-01 | Patient Mobile App (iOS + Android) | Could Have | High | 34 | Not Started | Phase 4 | Sprint 10 | App available on iOS 14+ and Android 9+; appointment & reports functional | F-17-01, F-17-03 | Appointments, reports, payments
|  | F-21-02 | Doctor Mobile App | Could Have | High | 21 | Not Started | Phase 4 | Sprint 10 | Doctor views schedule, dictates notes; syncs in real-time | F-18-01 | Schedule, consult notes on-the-go
|  | F-21-03 | Nurse Mobile App | Could Have | High | 21 | Not Started | Phase 4 | Sprint 10 | Nurse scans barcode to administer medication; records vitals | F-10-02 | MAR, vitals entry at bedside
|  | F-21-04 | Push Notifications (All Roles) | Could Have | Medium | 8 | Not Started | Phase 4 | Sprint 10 | Push sent on appointment confirm, lab result ready, bill generated | F-21-01, F-21-02, F-21-03 | Appointment, lab result, alert pushes
TOTAL · 117 Features | [5 empty] | 1203

## 🗓️ Sprint Plan
Sprint | Sprint Goal | Start Date | End Date | Story Points | Features Count | Status
Sprint 1 | Foundation: UHID, RBAC, Employee Master, Master Data | TBD | TBD | 58 | 5 | Not Started
Sprint 2 | Core patient flow: Appointments, Queue, OPD Billing, Queue Display | TBD | TBD | 97 | 9 | Not Started
Sprint 3 | EMR backbone: SOAP Notes, e-Prescription, Pharmacy Drug DB, Daily Reports | TBD | TBD | 125 | 13 | Not Started
Sprint 4 | Inpatient workflow: Beds, Admissions, Nursing MAR, Doctor Portal | TBD | TBD | 215 | 21 | Not Started
Sprint 5 | Lab system, Emergency Triage, Inventory, Patient Medical History | TBD | TBD | 172 | 21 | Not Started
Sprint 6 | Insurance billing, MIS Dashboard, Chronic Disease, Radiology Orders | TBD | TBD | 146 | 15 | Not Started
Sprint 7 | OT module, Pharmacy analytics, Lab analytics, Vendor comparison | TBD | TBD | 99 | 10 | Not Started
Sprint 8 | Machine interfacing, Biometric attendance, Lab QC, Anesthesia | TBD | TBD | 100 | 10 | Not Started
Sprint 9 | Blood bank module, Patient portal, Donor management | TBD | TBD | 73 | 6 | Not Started
Sprint 10 | DICOM/PACS, Custom reports, Mobile apps, Telemedicine, Voice-to-text | TBD | TBD | 147 | 7 | Not Started
TOTAL |  |  |  | 1232 | 117
SPRINT FEATURE BREAKDOWN
Sprint | Feature ID | Feature Name | Priority | Complexity | SP
Sprint 1 | F-01-01 | Patient Registration & UHID Generation | Must Have | High | 21
Sprint 1 | F-01-02 | Patient Search & Advanced Filter | Must Have | Medium | 8
Sprint 1 | F-13-01 | Employee Master | Must Have | Medium | 8
Sprint 1 | F-15-01 | Role-Based Access Control (RBAC) | Must Have | High | 13
Sprint 1 | F-15-03 | Master Data Management | Must Have | Low | 8
Sprint 2 | F-01-03 | Patient Demographics Management | Must Have | Medium | 13
Sprint 2 | F-02-01 | Doctor Schedule Configuration | Must Have | High | 13
Sprint 2 | F-02-02 | Online Appointment Booking | Must Have | Medium | 13
Sprint 2 | F-02-03 | Walk-in Registration & Token Generation | Must Have | Medium | 8
Sprint 2 | F-02-07 | Doctor Leave Management | Must Have | Medium | 8
Sprint 2 | F-03-01 | Patient Queue Management with Display Board | Must Have | Medium | 13
Sprint 2 | F-08-01 | OPD Billing & Receipt | Must Have | Medium | 13
Sprint 2 | F-08-03 | Payment Collection (Multi-Mode) | Must Have | Medium | 8
Sprint 2 | F-15-02 | Audit Trail & Activity Logs | Must Have | Medium | 8
Sprint 3 | F-01-04 | Merge Duplicate Patient Records | Should Have | High | 8
Sprint 3 | F-02-04 | Appointment Rescheduling & Cancellation | Should Have | Low | 5
Sprint 3 | F-02-06 | Appointment Waitlist Management | Must Have | Medium | 8
Sprint 3 | F-03-02 | Clinical Documentation (SOAP Notes) | Must Have | High | 21
Sprint 3 | F-03-03 | Vital Signs Recording | Must Have | Low | 5
Sprint 3 | F-03-04 | e-Prescription Writing | Must Have | High | 13
Sprint 3 | F-03-09 | Follow-up Scheduling from OPD | Must Have | Low | 5
Sprint 3 | F-07-01 | Drug Master Database | Must Have | High | 13
Sprint 3 | F-07-02 | Stock Management (GRN, Expiry Tracking) | Must Have | High | 21
Sprint 3 | F-07-06 | Generic ↔ Brand Mapping | Must Have | Medium | 5
Sprint 3 | F-08-07 | Discount & Concession Management | Must Have | Medium | 5
Sprint 3 | F-14-01 | Daily Collection Report | Must Have | Medium | 8
Sprint 3 | F-16-02 | Allergy Management | Must Have | Medium | 8
Sprint 4 | F-01-05 | Patient Photo & Document Upload | Could Have | Low | 5
Sprint 4 | F-03-05 | ICD-10 Code Integration | Should Have | Medium | 8
Sprint 4 | F-03-06 | Diagnosis & Prescription Templates | Should Have | Medium | 8
Sprint 4 | F-03-08 | Referral Management | Must Have | Medium | 8
Sprint 4 | F-03-10 | Procedure Recording | Must Have | Medium | 8
Sprint 4 | F-04-01 | Bed Management Dashboard | Must Have | High | 21
Sprint 4 | F-04-02 | Admission Process (Emergency/Planned) | Must Have | High | 13
Sprint 4 | F-04-03 | Ward Management & Bed Transfer | Must Have | Medium | 13
Sprint 4 | F-07-03 | Prescription Dispensing | Must Have | High | 13
Sprint 4 | F-07-07 | Drug Interaction Warning | Must Have | High | 13
Sprint 4 | F-07-08 | Controlled Drug Tracking | Must Have | High | 8
Sprint 4 | F-07-10 | Expiry & Near-Expiry Alerts | Must Have | Low | 5
Sprint 4 | F-08-02 | IPD Billing (Daily & Discharge) | Must Have | High | 21
Sprint 4 | F-08-08 | Credit & Advance Payment Management | Must Have | Medium | 8
Sprint 4 | F-10-01 | Nursing Assessment Forms | Must Have | Medium | 13
Sprint 4 | F-10-02 | Medication Administration Record (MAR) | Must Have | High | 13
Sprint 4 | F-10-03 | Vital Signs Charting (Trend View) | Must Have | Low | 8
Sprint 4 | F-18-01 | Doctor Dashboard | Must Have | Medium | 8
Sprint 4 | F-18-02 | Daily Appointment List | Must Have | Low | 5
Sprint 4 | F-18-03 | Patient History Review | Must Have | Medium | 8
Sprint 4 | F-18-04 | e-Prescription Templates | Must Have | Medium | 8
Sprint 5 | F-02-05 | SMS/Email Appointment Reminders | Could Have | Medium | 8
Sprint 5 | F-02-08 | QR Code Check-in | Should Have | Medium | 5
Sprint 5 | F-04-04 | Discharge Summary Generation | Must Have | Medium | 13
Sprint 5 | F-05-01 | Lab Test Catalog Setup | Must Have | High | 8
Sprint 5 | F-05-02 | Lab Order Entry (Internal/External) | Must Have | High | 13
Sprint 5 | F-05-03 | Sample Collection & Barcode System | Must Have | High | 13
Sprint 5 | F-05-07 | Reference Range Management | Must Have | Medium | 5
Sprint 5 | F-07-04 | Purchase Order Management | Should Have | Medium | 13
Sprint 5 | F-07-05 | Supplier Management | Should Have | Low | 5
Sprint 5 | F-07-09 | Auto Reorder Level Alerts | Must Have | Medium | 5
Sprint 5 | F-08-06 | Package & Bundle Billing | Must Have | Medium | 8
Sprint 5 | F-10-04 | Fluid Balance Chart | Should Have | Medium | 8
Sprint 5 | F-12-01 | Emergency Patient Registration | Must Have | Medium | 5
Sprint 5 | F-12-02 | Triage Assessment (CTAS/ESI) | Must Have | Medium | 8
Sprint 5 | F-16-01 | Longitudinal Patient Medical History | Must Have | High | 13
Sprint 5 | F-16-04 | Clinical Attachments & Scanned Records | Must Have | Medium | 8
Sprint 5 | F-19-01 | Medical Consumable Inventory | Must Have | Medium | 8
Sprint 5 | F-19-02 | Store Requisition | Must Have | Medium | 8
Sprint 5 | F-19-04 | Stock Adjustment | Must Have | Low | 5
Sprint 5 | F-19-05 | Purchase Requisition | Must Have | Medium | 8
Sprint 5 | F-20-01 | Insurance Company Master | Must Have | Low | 5
Sprint 6 | F-02-09 | Online Payment During Booking | Could Have | Low | 8
Sprint 6 | F-03-07 | Clinical Pathways | Should Have | High | 13
Sprint 6 | F-04-05 | Death Certificate Module | Should Have | Low | 5
Sprint 6 | F-05-04 | Result Entry & Verification (Dual Sign-off) | Must Have | Medium | 13
Sprint 6 | F-05-05 | Lab Report Generation (PDF) | Must Have | Medium | 8
Sprint 6 | F-05-08 | Critical Value Alerts | Must Have | Medium | 5
Sprint 6 | F-06-01 | Radiology Order Management | Must Have | Medium | 8
Sprint 6 | F-08-04 | Refund Processing | Should Have | Low | 5
Sprint 6 | F-08-05 | Corporate / Insurance Billing (TPA) | Must Have | High | 21
Sprint 6 | F-14-02 | MIS Executive Dashboard | Must Have | High | 13
Sprint 6 | F-14-03 | Occupancy & Revenue Reports | Must Have | Medium | 8
Sprint 6 | F-14-05 | Doctor Revenue & Productivity Report | Must Have | Medium | 8
Sprint 6 | F-16-03 | Chronic Disease Management | Must Have | High | 13
Sprint 6 | F-19-03 | Inter-Store Transfer | Should Have | Medium | 5
Sprint 6 | F-20-02 | Pre-Authorization Request | Must Have | High | 13
Sprint 7 | F-06-03 | Radiology Reporting Template | Must Have | Medium | 13
Sprint 7 | F-09-01 | OT Scheduling & Booking | Must Have | High | 13
Sprint 7 | F-09-02 | Surgery Notes & WHO Safety Checklist | Must Have | Medium | 13
Sprint 7 | F-14-06 | Patient Visit Trends | Should Have | Medium | 5
Sprint 7 | F-14-07 | Pharmacy Sales Analytics | Must Have | Medium | 8
Sprint 7 | F-14-08 | Lab Revenue Analytics | Must Have | Medium | 5
Sprint 7 | F-16-05 | Patient Timeline View | Should Have | Medium | 13
Sprint 7 | F-19-06 | Vendor Comparison & Rate Contract | Should Have | Medium | 8
Sprint 7 | F-20-03 | Claim Processing & Submission | Must Have | High | 13
Sprint 7 | F-20-04 | Claim Tracking & Status | Must Have | Medium | 8
Sprint 8 | F-05-06 | Machine Interfacing (ASTM/HL7) | Should Have | High | 21
Sprint 8 | F-05-09 | Delta Check Validation | Should Have | High | 8
Sprint 8 | F-09-03 | Anaesthesia Record | Should Have | Medium | 8
Sprint 8 | F-13-02 | Attendance Management | Should Have | Medium | 13
Sprint 8 | F-13-03 | Leave Management | Should Have | Low | 8
Sprint 8 | F-17-01 | Patient Login & Profile | Should Have | Medium | 13
Sprint 8 | F-17-02 | View Prescriptions Online | Should Have | Low | 8
Sprint 8 | F-17-03 | View & Download Lab Reports | Should Have | Low | 8
Sprint 8 | F-17-04 | Download Invoices & Receipts | Should Have | Low | 5
Sprint 8 | F-20-05 | Settlement & Reconciliation | Must Have | Medium | 8
Sprint 9 | F-05-10 | Lab Quality Control Module | Should Have | High | 13
Sprint 9 | F-11-01 | Donor Management | Should Have | Medium | 8
Sprint 9 | F-11-02 | Blood Inventory & Screening | Must Have | High | 13
Sprint 9 | F-11-03 | Cross Matching & Transfusion Record | Must Have | High | 13
Sprint 9 | F-17-05 | Online Payment via Portal | Should Have | Medium | 13
Sprint 9 | F-18-05 | Voice-to-Text Clinical Notes | Could Have | High | 13
Sprint 10 | F-06-02 | DICOM/PACS Integration | Should Have | High | 21
Sprint 10 | F-14-04 | Custom Report Builder | Could Have | High | 21
Sprint 10 | F-17-06 | Telemedicine Consultation | Could Have | High | 21
Sprint 10 | F-21-01 | Patient Mobile App (iOS + Android) | Could Have | High | 34
Sprint 10 | F-21-02 | Doctor Mobile App | Could Have | High | 21
Sprint 10 | F-21-03 | Nurse Mobile App | Could Have | High | 21
Sprint 10 | F-21-04 | Push Notifications (All Roles) | Could Have | Medium | 8

## 🏗️ Epic Summary
Epic ID | Epic Name | Must Have | Should Have | Could Have | Total Features | Total Story Points | Complexity
EPIC-01 | Patient Management | 3 | 1 | 1 | 5 | 55 | High×2
EPIC-02 | Appointment System | 5 | 2 | 2 | 9 | 76 | High×1
EPIC-03 | OPD Management | 7 | 3 | 0 | 10 | 102 | High×3
EPIC-04 | Inpatient Management | 4 | 1 | 0 | 5 | 65 | High×2
EPIC-05 | Laboratory Information System | 7 | 3 | 0 | 10 | 107 | High×6
EPIC-06 | Radiology Management | 2 | 1 | 0 | 3 | 42 | High×1
EPIC-07 | Pharmacy Management | 8 | 2 | 0 | 10 | 101 | High×5
EPIC-08 | Billing & Finance | 7 | 1 | 0 | 8 | 89 | High×2
EPIC-09 | Surgery & OT | 2 | 1 | 0 | 3 | 34 | High×1
EPIC-10 | Nursing Module | 3 | 1 | 0 | 4 | 42 | High×1
EPIC-11 | Blood Bank | 2 | 1 | 0 | 3 | 34 | High×2
EPIC-12 | Emergency & Triage | 2 | 0 | 0 | 2 | 13 | Medium/Low
EPIC-13 | HR & Staff Management | 1 | 2 | 0 | 3 | 29 | Medium/Low
EPIC-14 | Reports & Analytics | 6 | 1 | 1 | 8 | 76 | High×2
EPIC-15 | System Admin | 3 | 0 | 0 | 3 | 29 | High×1
EPIC-16 | Electronic Medical Records (EMR) | 4 | 1 | 0 | 5 | 55 | High×2
EPIC-17 | Patient Portal | 0 | 5 | 1 | 6 | 68 | High×1
EPIC-18 | Doctor Portal | 4 | 0 | 1 | 5 | 42 | High×1
EPIC-19 | Inventory Management | 4 | 2 | 0 | 6 | 42 | Medium/Low
EPIC-20 | Insurance & TPA | 5 | 0 | 0 | 5 | 47 | High×2
EPIC-21 | Mobile Applications | 0 | 0 | 4 | 4 | 84 | High×3
TOTAL |  | 79 | 28 | 10 | 117 | 1232